## Alectra all scenarios_Revised (hidden)
Illustrative Schedule for Alectra Utilities - 2027-2031 Custom IR Application
OEB File Number: EB-2025-0252
Updated: October 15, 2025
Stage | Step # | Procedural Steps | Performance Standard Days Elapsed | Performance Standard Date | Case Schedule Days Elapsed | Case Schedule Indicative Date* | Actual Date | Status | Comments | Proposed Case Schedule Days Elapsed | Proposed Case Schedule | Comments2
Completeness | 1 | Applicant files Application |  |  |  | 2025-10-14 |  |  |  |  | 2025-10-14
| 2 | OEB issues Acknowledgement Letter |  |  |  | 2025-10-15 |  |  |  |  | 2025-10-15
| 3 | OEB issues Completeness Letter |  |  | 0 | 2025-10-28 |  |  |  | 0 | 2025-10-28
Notice & Procedural Order No. 1 | 4 | OEB issues Notice of Hearing | 10 | 2025-11-07 | 3 | 2025-10-31 |  |  |  | 3 | 2025-10-31
| 6 | Applicant files Affidavit confirming service and publication | 15 | 2025-11-14 | 10 | 2025-11-07 |  |  |  | 10 | 2025-11-07
| 7 | Intervention requests | 40 | 2025-12-07 | 20 | 2025-11-17 |  |  |  | 20 | 2025-11-17
| 8 | OEB issues Procedural Order No. 1 | 60 | 2026-01-12 | 27 | 2025-11-24 |  |  |  | 23 | 2025-11-20
Issues List | 9 | Issues Conference |  |  | 34 | 2025-12-01 |  |  |  | 30 | 2025-11-27
| 10 | Submissions on Issues that parties unable to reach consensus |  |  | 38 | 2025-12-05 |  |  |  | 34 | 2025-12-01
| 11 | If agreement reached, OEB staff files proposed issues list |  |  | 38 | 2025-12-05 |  |  |  | 34 | 2025-12-01
Confidentiality | 12 | OEB staff and intervenors to file submissions on confidentiality, if any |  |  | 35 | 2025-12-02 |  |  |  | 35 | 2025-12-02
| 13 | Applicant to file reply submissions on confidentiality |  |  | 41 | 2025-12-08 |  |  |  | 41 | 2025-12-08
Intervenor/Staff Intent Letter on Expert Evidence | 14 | OEB staff and intervenor letters on intention to submit expert evidence |  |  | 45 | 2025-12-12 |  |  |  | 41 | 2025-12-08
HOLIDAY BREAK (DECEMBER 20, 2025 TO JANUARY 4, 2026 INCLUSIVE – 16 DAYS)
Discovery | 15 | OEB staff and intervenors file interrogatories | 90 | 2026-02-11 | 56 | 2026-01-08 |  |  |  | 51 | 2025-12-18
| 16 | Applicant files responses to interrogatories | 120 | 2026-03-13 | 85 | 2026-02-06 |  |  |  | 76 | 2026-01-28
| 17 | OEB staff and intervenors to file topic areas and time estimates for Technical Conference |  |  | 99 | 2026-02-20 |  |  |  | 89 | 2026-02-10 | *February 16 - Family Day
| 18 | Technical Conference | 130 |  | 109 | 2026-03-02 |  |  |  | 102 | 2026-02-23
| 19 | Technical Conference ends (5 days) |  | 2026-03-23 | 113 | 2026-03-06 |  |  |  | 106 | 2026-02-27
| 20 | Undertakings related to OEB staff and intervenor evidence Filed |  |  | 120 | 2026-03-13 |  |  |  | 110 | 2026-03-06
MARCH BREAK (March 16-20, 2026 )
| 21 | Motions Hearing held (Re Incomplete IRRs & Undertakings) |  |  | 130 | 2026-03-23 |  |  |  | 120 | 2026-03-13
| 22 | OEB staff and intervenors file expert evidence, if any | 140 | 2026-04-03 | 134 | 2026-03-27 |  |  |  | 125 | 2026-03-18
| 23 | Interrogatories on OEB staff/intervenor expert evidence | 147 | 2026-04-10 | 141 | 2026-04-03 |  |  |  | 132 | 2026-03-25
| 24 | OEB staff and intervenor responses to interrogatories on expert evidence filed | 155 | 2026-04-17 | 148 | 2026-04-10 |  |  |  | 139 | 2026-04-01
Scenario 1 - Full Settlement
| 25 | Settlement Conference begins | 165 | 2026-04-27 | 155 | 2026-04-17 |  |  |  | 144 | 2026-04-06
| 26 | Settlement Conference ends |  |  | 159 | 2026-04-21 |  |  |  | 148 | 2026-04-10
| 27 | Settlement Progress Letter filed |  |  | 162 | 2026-04-24 |  |  |  | 151 | 2026-04-13
| 28 | Settlement Proposal filed (FULL settlement) | 180 | 2026-05-12 | 180 | 2026-05-12 |  |  |  | 159 | 2026-04-21
| 29 | OEB staff submission on Settlement Proposal filed | 187 | 2026-05-19 | 187 | 2026-05-19 |  |  |  | 166 | 2026-06-01
| 30 | Decision issued | 355 | 2026-11-03 | 277 | 2026-08-17 |  |  |  | 257 | 2026-08-31
Scenario 2 - Substantial Settlement (1 Week Hearing)
| 25 | Settlement Conference begins | 165 | 2026-04-27 | 155 | 2026-04-17 |  |  |  | 144 | 2026-04-06
| 26 | Settlement Conference ends |  |  | 159 | 2026-04-21 |  |  |  | 148 | 2026-04-10
| 27 | Settlement Progress Letter filed |  |  | 162 | 2026-04-24 |  |  |  | 151 | 2026-04-13
| 28 | Settlement Proposal filed (SUBSTANTIAL Settlement) | 180 | 2026-05-12 | 180 | 2026-05-12 |  |  |  | 159 | 2026-04-21
| 29 | OEB staff submission on settlement proposal filed | 187 | 2026-05-19 | 187 | 2026-05-19 |  |  |  | 166 | 2026-05-01
| 30 | Presentation of settlement agreement & oral hearing on unsettled issues begins (5 Days) | 200 | 2026-06-01 | 200 | 2026-06-01 |  |  |  | 179 | 2026-05-11
| 31 | Oral Hearing ends |  |  | 204 | 2026-06-05 |  |  |  | 183 | 2026-05-15
| 32 | Undertakings from Oral Hearing filed |  |  | 211 | 2026-06-12 |  |  |  | 190 | 2026-05-22
| 33 | Argument-in-chief filed | 230 | 2026-07-03 | 229 | 2026-06-30 |  |  |  | 229 | 2026-06-30
| 34 | OEB staff and intervenor submissions filed | 250 | 2026-07-21 | 249 | 2026-07-20 |  |  |  | 249 | 2026-07-20
| 35 | Reply argument filed | 265 | 2026-08-07 | 264 | 2026-08-04 |  |  |  | 264 | 2026-08-04
| 36 | Decision issued | 355 | 2026-11-03 | 354 | 2026-11-02 |  |  |  | 354 | 2026-11-02
Scenario 3 - Partial Settlement (2 Week Hearing)
| 25 | Settlement Conference begins | 165 | 2026-04-27 | 155 | 2026-04-17 |  |  |  | 144 | 2026-04-06
| 26 | Settlement Conference ends |  |  | 159 | 2026-04-21 |  |  |  | 148 | 2026-04-10
| 27 | Settlement Progress Letter filed |  |  | 162 | 2026-04-24 |  |  |  | 151 | 2026-04-13
| 28 | Settlement Proposal filed (PARTIAL Settlement) | 180 | 2026-05-12 | 180 | 2026-05-12 |  |  |  | 159 | 2026-04-21
| 29 | OEB staff submission on Settlement Proposal filed | 187 | 2026-05-19 | 187 | 2026-05-19 |  |  |  | 166 | 2026-04-28
| 30 | Presentation of Settlement Agreement & Oral Hearing on unsettled issues begins (2 weeks) | 200 | 2026-06-01 | 200 | 2026-06-01 |  |  |  | 179 | 2026-05-11
| 31 | Oral Hearing Ends/Decision on Settlement Agreement |  |  | 213 | 2026-06-14 |  |  |  | 190 | 2026-05-22
| 32 | Undertakings from Oral Hearing filed |  |  | 220 | 2026-06-21 |  |  |  | 197 | 2026-05-29
| 33 | Argument-in-chief filed | 230 | 2026-07-03 | 229 | 2026-06-30 |  |  |  | 229 | 2026-06-30
| 34 | OEB staff and intervenor submissions filed | 250 | 2026-07-21 | 249 | 2026-07-20 |  |  |  | 249 | 2026-07-20
| 35 | Reply argument filed | 265 | 2026-08-07 | 264 | 2026-08-04 |  |  |  | 264 | 2026-08-04
| 36 | Decision issued | 355 | 2026-11-03 | 354 | 2026-11-02 |  |  |  | 354 | 2026-11-02
Scenario 4 - No Settlement (3.5 Week Hearing)
| 25 | Settlement Conference begins | 165 | 2026-04-27 | 155 | 2026-04-17 |  |  |  | 144 | 2026-04-06
| 26 | Settlement Conference ends |  |  | 159 | 2026-04-21 |  |  |  | 148 | 2026-04-10
| 27 | Letter reporting no settlement filed | 180 | 2026-05-12 | 162 | 2026-04-24 |  |  |  | 151 | 2026-04-13
| 28 | Oral Hearing on ALL Issues begins (3.5 weeks) | 200 | 2026-06-01 | 184 | 2026-05-16 |  |  |  | 159 | 2026-04-21
| 29 | Oral Hearing Ends |  |  | 208 | 2026-06-09 |  |  |  | 183 | 2026-05-15
| 30 | Undertakings from Oral Hearing filed |  |  | 215 | 2026-06-16 |  |  |  | 190 | 2026-05-22
| 31 | Argument-in-chief filed | 230 | 2026-07-03 | 225 | 2026-06-26 |  |  |  | 200 | 2026-06-01
| 32 | OEB staff and intervenor Submissions filed | 250 | 2026-07-21 | 246 | 2026-07-17 |  |  |  | 221 | 2026-06-22
| 33 | Reply Argument filed | 265 | 2026-08-07 | 261 | 2026-08-01 |  |  |  | 236 | 2026-07-07
| 34 | Decision issued | 355 | 2026-11-03 | 351 | 2026-10-30 |  |  |  | 326 | 2026-10-05
Notes:
* Indicative dates have not been approved by the OEB Panel. They are intended to be illustrative only, provided the individual steps take place.
Formulas:
Case Schedule Indicative Date* = [Case Schedule Indicative Date*, row above]+1
Case Schedule Indicative Date* = [Case Schedule Days Elapsed]+G7
Performance Standard Date = [Performance Standard Days Elapsed]+G7
Performance Standard Date = [Performance Standard Days Elapsed]+G7+2
Proposed Case Schedule = [Proposed Case Schedule Days Elapsed]+[Proposed Case Schedule, row above]
Proposed Case Schedule = [Proposed Case Schedule Days Elapsed]+L7

## Proposed schedule Scn 1 (hidden)
Illustrative Schedule for Alectra Utilities - 2027-2031 Custom IR Application
OEB File Number: EB-2025-0252
Updated: November 3, 2025
Stage | Step # | Procedural Steps | Performance Standard Days Elapsed | Performance Standard Date | Case Schedule Days Elapsed | Case Schedule Indicative Date* | Planned Case Schedule Days Elapsed | Case Schedule Indicative Date* (Scenario 2)
Completeness | 1 | Applicant files Application |  |  |  | 2025-10-14
| 2 | OEB issues Acknowledgement Letter |  |  |  | 2025-10-15
| 3 | OEB issues Completeness Letter |  |  | 0 | 2025-10-28
Notice & Procedural Order No. 1 | 4 | OEB issues Notice of Hearing | 10 | 2025-11-07 | 3 | 2025-10-31 | 3 | 2025-10-31
| 6 | Applicant files Affidavit confirming service and publication | 15 | 2025-11-12 | 10 | 2025-11-07 | 7 | 2025-11-04
| 7 | Intervention requests | 40 | 2025-12-08 | 20 | 2025-11-17 | 20 | 2025-11-17
| 8 | OEB issues Procedural Order No. 1 | 60 | 2026-01-12 | 27 | 2025-11-24 | 24 | 2025-11-21
Issues List | 9 | OEB Staff Files proposed Issues List |  |  | 41 | 2025-12-08 | 31 | 2025-11-28
| 10 | Submissions on Issues that parties unable to reach consensus |  |  | 45 | 2025-12-12 | 35 | 2025-12-02
| 11 | If agreement reached, OEB staff files proposed issues list |  |  | 45 | 2025-12-12 | 35 | 2025-12-02
Confidentiality | 12 | OEB staff and intervenors to file submissions on confidentiality, if any |  |  | 36 | 2025-12-03 | 31 | 2025-11-28
| 13 | Applicant to file reply submissions on confidentiality |  |  | 43 | 2025-12-10 | 38 | 2025-12-05
Intervenor/Staff Intent Letter on Expert Evidence | 14 | OEB staff and intervenor letters on intention to submit expert evidence |  |  | 43 | 2025-12-10 | 43 | 2025-12-10
HOLIDAY BREAK (DECEMBER 20, 2025 TO JANUARY 4, 2026 INCLUSIVE – 16 DAYS)
Discovery | 15 | OEB staff and intervenors file interrogatories | 90 | 2026-02-11 | 60 | 2026-01-12 | 60 | 2026-01-12
| 16 | Applicant files responses to interrogatories | 120 | 2026-03-13 | 88 | 2026-02-09 | 88 | 2026-02-09
| 17 | OEB staff and intervenors to file topic areas and time estimates for Technical Conference |  |  | 99 | 2026-02-20 | 99 | 2026-02-20
| 18 | Technical Conference | 130 | 2026-03-23 | 103 | 2026-02-24 | 103 | 2026-02-24 | During the meeting with Alectra, the technical conference was summed to start on March 23, 2026
| 19 | Technical Conference ends (5 days) |  |  | 109 | 2026-03-02 | 109 | 2026-03-02
| 20 | Undertakings related to OEB staff and intervenor evidence Filed |  |  | 116 | 2026-03-09 | 116 | 2026-03-09
|  | Applicant files final DVA Continuity Schedule and other items |  |  | 118 | 2026-03-11 | 118 | 2026-03-11 | ***Everything has to be finalized for Pauline to review***This is a separate process to accommodate the delay in providing the updated DVA Continuity Schedule and other items
|  | OEB staff and intervenors file motions letter |  |  | 119 | 2026-03-12 | 119 | 2026-03-12
| 21 | Motions Hearing held (Re Incomplete IRRs & Undertakings) |  |  | 120 | 2026-03-13 | 120 | 2026-03-13 | At least 4 days from Undertaking responses
MARCH BREAK (March 16-20, 2026 )
|  | OEB staff and intervenors file interrogatories on DVA Continuity Schedule and other items |  |  | 132 | 2026-03-25 | 132 | 2026-03-25
| 22 | OEB staff and intervenors file expert evidence, if any | 140 | 2026-04-02 | 137 | 2026-03-30 | 137 | 2026-03-30
|  | Applicant files responses to interrogatories on DVA Continuity Schedule and other items |  |  | 139 | 2026-04-01 | 139 | 2026-04-01
| 23 | Interrogatories on OEB staff/intervenor expert evidence | 147 | 2026-04-09 | 145 | 2026-04-07 | 145 | 2026-04-07 | April 3 is Good Friday
| 24 | OEB staff and intervenor responses to interrogatories on expert evidence filed | 155 | 2026-04-17 | 152 | 2026-04-14 | 152 | 2026-04-14
|  | Deadline to send pre-settlement conference clarification questions |  |  | 155 | 2026-04-17 | 155 | 2026-04-17 | Internal only***Pre-settlement conference clarification questions can be sent earlier and in several rounds until a day before the start of the settlement conference
Scenario 1 - Full Settlement
| 25 | Settlement Conference begins | 165 | 2026-04-27 | 158 | 2026-04-20 | 158 | 2026-04-20
| 26 | Settlement Conference ends |  |  | 162 | 2026-04-24 | 162 | 2026-04-24
| 27 | Settlement Progress Letter filed |  |  | 166 | 2026-04-28 | 166 | 2026-04-28
| 28 | Settlement Proposal filed (FULL settlement) | 180 | 2026-05-12 | 183 | 2026-05-15 | 183 | 2026-05-15
| 29 | OEB staff submission on Settlement Proposal filed | 187 | 2026-05-19 | 193 | 2026-05-25 | 193 | 2026-05-25
| 30 | Decision issued | 355 | 2026-11-03 | 284 | 2026-08-24 | 284 | 2026-08-24
Scenario 2 - Substantial Settlement (1 Week Hearing)
| 25 | Settlement Conference begins | 165 | 2026-04-27 | 158 | 2026-04-20 | 158 | 2026-04-20
| 26 | Settlement Conference ends |  |  | 162 | 2026-04-24 | 162 | 2026-04-24
| 27 | Settlement Progress Letter filed |  |  | 166 | 2026-04-28 | 166 | 2026-04-28
| 28 | Settlement Proposal filed (SUBSTANTIAL Settlement) | 180 | 2026-05-12 | 183 | 2026-05-15 | 183 | 2026-05-15
| 29 | OEB staff submission on settlement proposal filed | 187 | 2026-05-19 | 193 | 2026-05-25 | 193 | 2026-05-25
| 30 | Presentation of settlement agreement & oral hearing on unsettled issues begins (5 Days) | 200 | 2026-06-01 | 207 | 2026-06-08 | 207 | 2026-06-08
| 31 | Oral Hearing ends |  |  | 211 | 2026-06-12 | 211 | 2026-06-12
| 32 | Undertakings from Oral Hearing filed |  |  | 218 | 2026-06-19 | 218 | 2026-06-19
| 33 | Argument-in-chief filed | 230 | 2026-07-02 | 230 | 2026-07-02 | 230 | 2026-07-02 | July 1 is Canada Day
| 34 | OEB staff and intervenor submissions filed | 250 | 2026-07-21 | 250 | 2026-07-21 | 250 | 2026-07-21
| 35 | Reply argument filed | 265 | 2026-08-05 | 265 | 2026-08-05 | 265 | 2026-08-05
| 36 | Decision issued | 355 | 2026-11-03 | 355 | 2026-11-03 | 355 | 2026-11-03
Scenario 3 - Partial Settlement (2 Week Hearing)
| 25 | Settlement Conference begins | 165 | 2026-04-27 | 158 | 2026-04-20 | 158 | 2026-04-20
| 26 | Settlement Conference ends |  |  | 162 | 2026-04-24 | 162 | 2026-04-24
| 27 | Settlement Progress Letter filed |  |  | 166 | 2026-04-28 | 166 | 2026-04-28
| 28 | Settlement Proposal filed (PARTIAL Settlement) | 180 | 2026-05-12 | 180 | 2026-05-12 | 180 | 2026-05-12
| 29 | OEB staff submission on Settlement Proposal filed | 187 | 2026-05-19 | 190 | 2026-05-22 | 190 | 2026-05-22 | May 18 is Victoria Day
| 30 | Presentation of Settlement Agreement & Oral Hearing on unsettled issues begins (2 weeks) | 200 | 2026-06-01 | 202 | 2026-06-03 | 202 | 2026-06-03
| 31 | Oral Hearing Ends/Decision on Settlement Agreement |  |  | 216 | 2026-06-17 | 216 | 2026-06-17
| 32 | Undertakings from Oral Hearing filed |  |  | 223 | 2026-06-24 | 223 | 2026-06-24
| 33 | Argument-in-chief filed | 230 | 2026-07-02 | 231 | 2026-07-02 | 231 | 2026-07-02 | July 1 is Canada Day
| 34 | OEB staff and intervenor submissions filed | 250 | 2026-07-21 | 250 | 2026-07-21 | 250 | 2026-07-21
| 35 | Reply argument filed | 265 | 2026-08-05 | 265 | 2026-08-05 | 265 | 2026-08-05
| 36 | Decision issued | 355 | 2026-11-03 | 355 | 2026-11-03 | 355 | 2026-11-03
Scenario 4 - No Settlement (3.5 Week Hearing)
| 25 | Settlement Conference begins | 165 | 2026-04-27 | 158 | 2026-04-20 | 158 | 2026-04-20
| 26 | Settlement Conference ends |  |  | 162 | 2026-04-24 | 162 | 2026-04-24
| 27 | Letter reporting no settlement filed | 180 | 2026-05-12 | 166 | 2026-04-28 | 166 | 2026-04-28
| 28 | Oral Hearing on ALL Issues begins (3.5 weeks) | 200 | 2026-06-01 | 187 | 2026-05-19 | 187 | 2026-05-19 | May 18 is Victoria Day
| 29 | Oral Hearing Ends |  |  | 211 | 2026-06-12 | 211 | 2026-06-12
| 30 | Undertakings from Oral Hearing filed |  |  | 218 | 2026-06-19 | 218 | 2026-06-19
| 31 | Argument-in-chief filed | 230 | 2026-07-02 | 232 | 2026-07-03 | 232 | 2026-07-03
| 32 | OEB staff and intervenor Submissions filed | 250 | 2026-07-21 | 250 | 2026-07-21 | 250 | 2026-07-21
| 33 | Reply Argument filed | 265 | 2026-08-05 | 265 | 2026-08-05 | 265 | 2026-08-05 | Aug 3 is Civic Day
| 34 | Decision issued | 355 | 2026-11-03 | 355 | 2026-11-03 | 355 | 2026-11-03
Notes:
* Indicative dates have not been approved by the OEB Panel. They are intended to be illustrative only, provided the individual steps take place.
Formulas:
Case Schedule Indicative Date* = [Case Schedule Indicative Date*, row above]+1
Case Schedule Indicative Date* = [Case Schedule Days Elapsed]+G7
Performance Standard Date = [Performance Standard Days Elapsed]+G7
Performance Standard Date = [Performance Standard Days Elapsed]+G7+1
Note on I11: Narisa Jotiban: PO1 can be issued on November 21, instead of 24 if there is no objection for intervenor requests from Alectra

## Proposed schedule Scn 2 (hidden)
Illustrative Schedule for Alectra Utilities - 2027-2031 Custom IR Application
OEB File Number: EB-2025-0252
Updated: November 24, 2025
Stage | Step # | Procedural Steps | Performance Standard Days Elapsed | Performance Standard Date | Case Schedule Days Elapsed | Case Schedule Indicative Date* (Scenario 1) | Planned Case Schedule Days Elapsed | Case Schedule Indicative Date* (Scenario 2)
Completeness | 1 | Applicant files Application |  |  |  | 2025-10-14
| 2 | OEB issues Acknowledgement Letter |  |  |  | 2025-10-15
| 3 | OEB issues Completeness Letter |  |  | 0 | 2025-10-28
Notice & Procedural Order No. 1 | 4 | OEB issues Notice of Hearing | 10 | 2025-11-07 | 3 | 2025-10-31 | 3 | 2025-10-31
| 6 | Applicant files Affidavit confirming service and publication | 15 | 2025-11-12 | 5 | 2025-11-05 | 7 | 2025-11-04
| 7 | Interventions Close | 40 | 2025-12-08 | 20 | 2025-11-17 | 20 | 2025-11-17
| 8 | OEB issues Procedural Order No. 1 | 60 | 2026-01-12 | 28 | 2025-11-25 | 24 | 2025-11-21
Issues List | 9 | OEB Staff Files proposed Issues List | 70 | 2026-01-22 | 42 | 2025-12-09 | 31 | 2025-11-28
| 10 | Submissions on Issues that parties unable to reach consensus |  |  | 44 | 2025-12-11 | 35 | 2025-12-02
| 11 | If agreement reached, OEB staff files proposed issues list |  |  | 44 | 2025-12-11 | 35 | 2025-12-02
Confidentiality | 12 | OEB staff and intervenors to file submissions on confidentiality, if any |  |  | 37 | 2025-12-04 | 31 | 2025-11-28
| 13 | Applicant to file reply submissions on confidentiality |  |  | 44 | 2025-12-11 | 38 | 2025-12-05
HOLIDAY BREAK (DECEMBER 20, 2025 TO JANUARY 4, 2026 INCLUSIVE – 16 DAYS)
Intervenor/Staff Intent Letter on Expert Evidence | 14 | OEB staff and intervenor letters on intention to submit expert evidence |  |  | 64 | 2026-01-16
Discovery | 15 | OEB staff and intervenors file the first set of interrogatories | 90 | 2026-02-11 | 70 | 2026-01-22 | 70 | 2026-01-22
| 16 | Applicant files responses to the first set of interrogatories | 120 | 2026-03-13 | 99 | 2026-02-20 | 99 | 2026-02-20
| 17 | OEB staff and intervenors to file topic areas and time estimates for Technical Conference |  |  | 109 | 2026-03-02
| 18 | Technical Conference | 130 | 2026-03-23 | 111 | 2026-03-04
| 19 | Technical Conference ends (5 days) |  |  | 117 | 2026-03-10
| 20 | Applicant files the 2025 actual information as directed in Procedural No. 1 |  |  | 118 | 2026-03-11 |  |  | ***Everything has to be finalized for Pauline to review***This is a separate process to accommodate the delay in providing the updated DVA Continuity Schedule and other items
MARCH BREAK (March 16-20, 2026 )
| 21 | OEB staff and intervenors file the second set of interrogatories |  |  | 132 | 2026-03-25
| 22 | Alectra files undertaking responses related to the Technical Conference |  |  | 133 | 2026-03-26 | #REF! | #REF!
| 23 | OEB staff and intervenors file motions letter on the first set of interrogatories and undertakings |  |  | 137 | 2026-03-30
| 24 | Motions Hearing held (Re Incomplete IRRs & Undertakings) |  |  | 138 | 2026-03-31 |  |  | April 3 is Good Friday
| 25 | Alectra files responses to the second set of interrogatories on Group 1 DVA |  |  | 146 | 2026-04-08 |  |  | Alectra needs 2 weeks
| 26 | OEB staff and intervenors file expert evidence, if any | 140 | 2026-04-02 | 148 | 2026-04-10
| 27 | OEB and Intervenors file clarification questions on the second set of IRs. |  |  | 153 | 2026-04-15
| 28 | Interrogatories on OEB staff/intervenor expert evidence | 147 | 2026-04-09 | 155 | 2026-04-17 | #REF! | #REF!
| 29 | Alectra Utilities files responses to the clarification questions on the second set of interrogatory responses |  |  | 160 | 2026-04-22
| 30 | OEB staff and intervenor responses to interrogatories on expert evidence filed | 155 | 2026-04-17 | 162 | 2026-04-24 | #REF! | #REF!
|  | Deadline to send pre-settlement conference clarification questions |  |  | 155 | 2026-04-17 |  |  | Internal only***Pre-settlement conference clarification questions can be sent in several rounds up to a day before the settlement conference
Scenario 1 - Substantial Settlement (1 Week Hearing)
| 31 | Settlement Conference begins | 165 | 2026-04-27 | 167 | 2026-04-29 | 167 | 2026-04-29
| 32 | Settlement Conference ends |  |  | 173 | 2026-05-05 | 173 | 2026-05-05
| 33 | Settlement Progress Letter filed |  |  | 173 | 2026-05-05 | 173 | 2026-05-05
| 34 | Settlement Conference continues (3 additional days if required) |  |  | 174 | 2026-05-06
| 35 | Settlement Proposal filed (SUBSTANTIAL Settlement) | 180 | 2026-05-12 | 194 | 2026-05-26 | 194 | 2026-05-26 | May 18 is Victoria Day
| 36 | OEB staff submission on settlement proposal filed | 187 | 2026-05-19 | 204 | 2026-06-05 | 204 | 2026-06-05
| 37 | Presentation of settlement agreement & oral hearing on unsettled issues begins (5 Days) | 200 | 2026-06-01 | 214 | 2026-06-15 | 214 | 2026-06-15
| 38 | Oral Hearing ends |  |  | 218 | 2026-06-19 | 218 | 2026-06-19
| 39 | Undertakings from Oral Hearing filed |  |  | 225 | 2026-06-26 | 225 | 2026-06-26
| 40 | Argument-in-chief filed | 230 | 2026-07-02 | 230 | 2026-07-02 | 230 | 2026-07-01 | July 1 is Canada Day
| 41 | OEB staff and intervenor submissions filed | 250 | 2026-07-21 | 250 | 2026-07-21 | 250 | 2026-07-21
| 42 | Reply argument filed | 265 | 2026-08-05 | 265 | 2026-08-05 | 265 | 2026-08-05 | Aug 3 is Civic Day
| 43 | Decision issued | 355 | 2026-11-03 | 355 | 2026-11-03 | 355 | 2026-11-03
Scenario 2 - No Settlement (3.5 Week Hearing)
| 31 | Settlement Conference begins | 165 | 2026-04-27 | 167 | 2026-04-29 | 167 | 2026-04-29
| 32 | Settlement Conference ends |  |  | 173 | 2026-05-05 | 173 | 2026-05-05
| 33 | Letter reporting no settlement filed | 180 | 2026-05-12 | 173 | 2026-05-05 | 173 | 2026-05-05
| 34 | Oral Hearing on ALL Issues begins (3.5 weeks) | 200 | 2026-06-01 | 193 | 2026-05-25 | 193 | 2026-05-25 | May 18 is Victoria Day
| 35 | Oral Hearing Ends |  |  | 217 | 2026-06-18 | 217 | 2026-06-18
| 36 | Undertakings from Oral Hearing filed |  |  | 224 | 2026-06-25 | 224 | 2026-06-25
| 37 | Argument-in-chief filed | 230 | 2026-07-02 | 230 | 2026-07-02 | 230 | 2026-07-01
| 38 | OEB staff and intervenor Submissions filed | 250 | 2026-07-21 | 250 | 2026-07-21 | 250 | 2026-07-21
| 39 | Reply Argument filed | 265 | 2026-08-05 | 265 | 2026-08-05 | 265 | 2026-08-05 | Aug 3 is Civic Day
| 40 | Decision issued | 355 | 2026-11-03 | 355 | 2026-11-03 | 355 | 2026-11-03
Scenario 3 - Partial Settlement (2 Week Hearing)
| 31 | Settlement Conference begins | 165 | 2026-04-27 | 167 | 2026-04-29 | 167 | 2026-04-29
| 32 | Settlement Conference ends |  |  | 173 | 2026-05-05 | 173 | 2026-05-05
| 33 | Settlement Progress Letter filed |  |  | 173 | 2026-05-05 | 173 | 2026-05-05
| 34 | Settlement Conference continues (3 additional days if required) |  |  | 174 | 2026-05-06
| 35 | Settlement Proposal filed (PARTIAL Settlement) | 180 | 2026-05-12 | 189 | 2026-05-21 | 189 | 2026-05-21 | May 18 is Victoria Day
| 36 | OEB staff submission on Settlement Proposal filed | 187 | 2026-05-19 | 196 | 2026-05-28 | 196 | 2026-05-28
| 37 | Presentation of Settlement Agreement & Oral Hearing on unsettled issues begins (2 weeks) | 200 | 2026-06-01 | 207 | 2026-06-08 | 207 | 2026-06-08
| 38 | Oral Hearing Ends/Decision on Settlement Agreement |  |  | 221 | 2026-06-22 | 221 | 2026-06-22
| 39 | Undertakings from Oral Hearing filed |  |  | 228 | 2026-06-29 | 228 | 2026-06-29
| 40 | Argument-in-chief filed | 230 | 2026-07-02 | 230 | 2026-07-02 | 230 | 2026-07-01 | July 1 is Canada Day
| 41 | OEB staff and intervenor submissions filed | 250 | 2026-07-21 | 250 | 2026-07-21 | 250 | 2026-07-21
| 42 | Reply argument filed | 265 | 2026-08-05 | 265 | 2026-08-05 | 265 | 2026-08-05 | Aug 3 is Civic Day
| 43 | Decision issued | 355 | 2026-11-03 | 355 | 2026-11-03 | 355 | 2026-11-03
Scenario 4 - Full Settlement
| 31 | Settlement Conference begins | 165 | 2026-04-27 | 167 | 2026-04-29 | 158 | 2026-04-20
| 32 | Settlement Conference ends |  |  | 173 | 2026-05-05 | 162 | 2026-04-24
| 33 | Settlement Progress Letter filed |  |  | 173 | 2026-05-05 | 166 | 2026-04-28
| 34 | Settlement Conference continues (3 additional days if required) |  |  | 174 | 2026-05-06
| 35 | Settlement Proposal filed (FULL settlement) | 180 | 2026-05-12 | 194 | 2026-05-26 | 183 | 2026-05-15
| 36 | OEB staff submission on Settlement Proposal filed | 187 | 2026-05-19 | 204 | 2026-06-05 | 204 | 2026-06-05
| 37 | Decision issued | 355 | 2026-11-03 | 295 | 2026-09-04 | 295 | 2026-09-04
Notes:
* Indicative dates have not been approved by the OEB Panel. They are intended to be illustrative only, provided the individual steps take place.
Formulas:
Performance Standard Date = [Performance Standard Days Elapsed]+G7
Performance Standard Date = [Performance Standard Days Elapsed]+G7+1
Note on I11: Narisa Jotiban: PO1 can be issued on November 21, instead of 24 if there is no objection for intervenor requests from Alectra

## Alectra Utilities
Schedule for Alectra Utilities - 2027-2031 Custom IR Application
OEB File Number: EB-2025-0252
Updated: February 5, 2026
Stage | Step # | Procedural Steps | Performance Standard Days Elapsed | Performance Standard Date | Case Schedule Days Elapsed | Case Schedule Indicative Date* (Scenario 1) | Planned Case Schedule Days Elapsed | Case Schedule Indicative Date* (Scenario 2) | Actual Date | Status | Comments
Completeness | 1 | Applicant files Application |  |  |  | 2025-10-14 |  |  | 2025-10-10 | 100%
| 2 | OEB issues Acknowledgement Letter |  |  |  | 2025-10-15 |  |  | 2025-10-10 | 100%
| 3 | OEB issues Completeness Letter |  |  | 0 | 2025-10-28 |  |  | 2025-10-24 | 100%
Notice & Procedural Order No. 1 | 4 | OEB issues Notice of Hearing | 10 | 2025-11-07 | 3 | 2025-10-31 | 3 | 2025-10-31 | 2025-10-31 | 100%
| 5 | Applicant files Affidavit confirming service and publication | 15 | 2025-11-12 | 5 | 2025-11-05 | 7 | 2025-11-04 | 2025-11-10 | 100%
| 6 | Interventions Close | 40 | 2025-12-08 | 20 | 2025-11-17 | 20 | 2025-11-17 | 2025-11-17 | 100%
| 7 | OEB issues Procedural Order No. 1 | 60 | 2026-01-12 | 45 | 2025-12-12 | 24 | 2025-11-21 | 2025-12-12 | 100%
Confidentiality | 8 | OEB staff and intervenors to file submissions on confidentiality, if any |  |  | 52 | 2025-12-19 | 31 | 2025-11-28 | 2025-12-19 | 100%
HOLIDAY BREAK (DECEMBER 20, 2025 TO JANUARY 4, 2026 INCLUSIVE – 16 DAYS)
| 9 | Applicant to file reply submissions on confidentiality |  |  | 57 | 2026-01-09
| 10 | OEB Staff Files proposed Issues List | 70 | 2026-01-22 | 61 | 2026-01-13 |  |  | 2026-01-12 | 100%
Discovery | 11 | OEB staff and intervenors file the first set of interrogatories | 90 | 2026-02-11 | 70 | 2026-01-22 | 70 | 2026-01-22 | 2026-01-22 | 100%
| 12 | OEB staff and intervenor letters on intention to submit expert evidence |  |  | 78 | 2026-01-30 |  |  | 2026-01-30 | 100%
| 13 | Applicant files responses to the first set of interrogatories | 120 | 2026-03-13 | 99 | 2026-02-20 | 99 | 2026-02-20
| 14 | OEB staff and intervenors to file topic areas and time estimates for Technical Conference |  |  | 109 | 2026-03-02
| 15 | Technical Conference | 130 | 2026-03-23 | 112 | 2026-03-05
| 16 | Technical Conference ends (5 days) |  |  | 118 | 2026-03-11
| 17 | Applicant files the 2025 actual information as directed in Procedural No. 1 |  |  | 118 | 2026-03-11
MARCH BREAK (March 16-20, 2026 )
| 18 | OEB staff and intervenors file the second set of interrogatories |  |  | 132 | 2026-03-25
| 19 | Alectra files undertaking responses related to the Technical Conference |  |  | 134 | 2026-03-27 | #REF! | #REF!
| 23 | OEB staff and intervenors file motions letter on the first set of interrogatories and undertakings |  |  | 139 | 2026-04-01
| 24 | Motions Hearing held (Re Incomplete IRRs & Undertakings) |  |  | 140 | 2026-04-02
| 20 | Alectra files responses to the second set of interrogatories |  |  | 146 | 2026-04-08
| 21 | OEB staff and intervenors file expert evidence, if any | 140 | 2026-04-02 | 148 | 2026-04-10
| 22 | OEB and Intervenors file clarification questions on the second set of IRs. |  |  | 153 | 2026-04-15
| 23 | Interrogatories on OEB staff/intervenor expert evidence | 147 | 2026-04-09 | 155 | 2026-04-17 | #REF! | #REF!
| 24 | Alectra Utilities files responses to the clarification questions on the second set of interrogatory responses |  |  | 160 | 2026-04-22
| 25 | OEB staff and intervenor responses to interrogatories on expert evidence filed | 155 | 2026-04-17 | 162 | 2026-04-24 | #REF! | #REF!
Scenario 1 - Substantial Settlement (1 Week Hearing)
| 26 | Settlement Conference begins | 165 | 2026-04-27 | 167 | 2026-04-29 | 167 | 2026-04-29
| 27 | Settlement Conference ends |  |  | 173 | 2026-05-05 | 173 | 2026-05-05
| 28 | Settlement Progress Letter filed |  |  | 173 | 2026-05-05 | 173 | 2026-05-05
| 29 | Potential additional settlement days begin |  |  | 174 | 2026-05-06 | 2026-05-22 | 2026-06-07
| 30 | Potential additional settlement days end |  |  | 176 | 2026-05-08
| 31 | Settlement Proposal filed (SUBSTANTIAL Settlement) | 180 | 2026-05-12 | 194 | 2026-05-26 | 194 | 2026-05-26
| 32 | OEB staff submission on settlement proposal filed | 187 | 2026-05-19 | 204 | 2026-06-05 | 204 | 2026-06-05
| 33 | Presentation of settlement agreement & oral hearing on unsettled issues begins (5 Days) | 200 | 2026-06-01 | 214 | 2026-06-15 | 214 | 2026-06-15
| 34 | Oral Hearing ends |  |  | 218 | 2026-06-19 | 218 | 2026-06-19
| 35 | Undertakings from Oral Hearing filed |  |  | 225 | 2026-06-26 | 225 | 2026-06-26
| 36 | Argument-in-chief filed | 230 | 2026-07-02 | 230 | 2026-07-02 | 230 | 2026-07-01
| 37 | OEB staff and intervenor submissions filed | 250 | 2026-07-21 | 250 | 2026-07-21 | 250 | 2026-07-21
| 38 | Reply argument filed | 265 | 2026-08-05 | 265 | 2026-08-05 | 265 | 2026-08-05
| 39 | Decision issued | 355 | 2026-11-03 | 355 | 2026-11-03 | 355 | 2026-11-03
Scenario 2 - No Settlement (3.5 Week Hearing)
| 40 | Settlement Conference begins | 165 | 2026-04-27 | 167 | 2026-04-29 | 167 | 2026-04-29
| 41 | Settlement Conference ends |  |  | 173 | 2026-05-05 | 173 | 2026-05-05
| 42 | Letter reporting no settlement filed | 180 | 2026-05-12 | 173 | 2026-05-05 | 173 | 2026-05-05
| 43 | Oral Hearing on ALL Issues begins (3.5 weeks) | 200 | 2026-06-01 | 193 | 2026-05-25 | 193 | 2026-05-25
| 44 | Oral Hearing Ends |  |  | 217 | 2026-06-18 | 217 | 2026-06-18
| 45 | Undertakings from Oral Hearing filed |  |  | 224 | 2026-06-25 | 224 | 2026-06-25
| 46 | Argument-in-chief filed | 230 | 2026-07-02 | 230 | 2026-07-02 | 230 | 2026-07-01
| 47 | OEB staff and intervenor Submissions filed | 250 | 2026-07-21 | 250 | 2026-07-21 | 250 | 2026-07-21
| 48 | Reply Argument filed | 265 | 2026-08-05 | 265 | 2026-08-05 | 265 | 2026-08-05
| 49 | Decision issued | 355 | 2026-11-03 | 355 | 2026-11-03 | 355 | 2026-11-03
Scenario 3 - Partial Settlement (2 Week Hearing)
| 50 | Settlement Conference begins | 165 | 2026-04-27 | 167 | 2026-04-29 | 167 | 2026-04-29
| 51 | Settlement Conference ends |  |  | 173 | 2026-05-05 | 173 | 2026-05-05
| 52 | Settlement Progress Letter filed |  |  | 173 | 2026-05-05 | 173 | 2026-05-05
| 53 | Potential additional settlement days begin |  |  | 174 | 2026-05-06
| 54 | Potential additional settlement days end |  |  | 176 | 2026-05-08
| 55 | Settlement Proposal filed (PARTIAL Settlement) | 180 | 2026-05-12 | 189 | 2026-05-21 | 189 | 2026-05-21
| 56 | OEB staff submission on Settlement Proposal filed | 187 | 2026-05-19 | 196 | 2026-05-28 | 196 | 2026-05-28
| 57 | Presentation of Settlement Agreement & Oral Hearing on unsettled issues begins (2 weeks) | 200 | 2026-06-01 | 207 | 2026-06-08 | 207 | 2026-06-08
| 58 | Oral Hearing Ends/Decision on Settlement Agreement |  |  | 221 | 2026-06-22 | 221 | 2026-06-22
| 59 | Undertakings from Oral Hearing filed |  |  | 228 | 2026-06-29 | 228 | 2026-06-29
| 60 | Argument-in-chief filed | 230 | 2026-07-02 | 230 | 2026-07-02 | 230 | 2026-07-01
| 61 | OEB staff and intervenor submissions filed | 250 | 2026-07-21 | 250 | 2026-07-21 | 250 | 2026-07-21
| 62 | Reply argument filed | 265 | 2026-08-05 | 265 | 2026-08-05 | 265 | 2026-08-05
| 63 | Decision issued | 355 | 2026-11-03 | 355 | 2026-11-03 | 355 | 2026-11-03
Scenario 4 - Full Settlement
| 64 | Settlement Conference begins | 165 | 2026-04-27 | 167 | 2026-04-29 | 158 | 2026-04-20
| 65 | Settlement Conference ends |  |  | 173 | 2026-05-05 | 162 | 2026-04-24
| 66 | Settlement Progress Letter filed |  |  | 173 | 2026-05-05 | 166 | 2026-04-28
| 67 | Settlement Conference continues (3 additional days if required) |  |  | 174 | 2026-05-06
| 68 | Potential additional settlement days end |  |  | 176 | 2026-05-08
| 69 | Settlement Proposal filed (FULL settlement) | 180 | 2026-05-12 | 194 | 2026-05-26 | 183 | 2026-05-15
| 70 | OEB staff submission on Settlement Proposal filed | 187 | 2026-05-19 | 204 | 2026-06-05 | 204 | 2026-06-05
| 71 | Decision issued | 355 | 2026-11-03 | 295 | 2026-09-04 | 295 | 2026-09-04
Notes:
* Indicative dates have not been approved by the OEB Panel. They are intended to be illustrative only, provided the individual steps take place.
Formulas:
Performance Standard Date = [Performance Standard Days Elapsed]+G7
Performance Standard Date = [Performance Standard Days Elapsed]+G7+1
Note on I11: Narisa Jotiban: PO1 can be issued on November 21, instead of 24 if there is no objection for intervenor requests from Alectra

## Proposed schedule_for BN (hidden)
Illustrative Schedule for Alectra Utilities - 2027-2031 Custom IR Application
OEB File Number: EB-2025-0252
Updated: November 26, 2025
Stage | Step # | Procedural Steps | Performance Standard Days Elapsed | Performance Standard Date | Case Schedule Days Elapsed | Case Schedule Indicative Date* (Scenario 1) | Planned Case Schedule Days Elapsed | Case Schedule Indicative Date* (Scenario 2)
Completeness | 1 | Applicant files Application |  |  |  | 2025-10-14
| 2 | OEB issues Acknowledgement Letter |  |  |  | 2025-10-15
| 3 | OEB issues Completeness Letter |  |  | 0 | 2025-10-28
Notice & Procedural Order No. 1 | 4 | OEB issues Notice of Hearing | 10 | 2025-11-07 | 3 | 2025-10-31 | 3 | 2025-10-31
| 6 | Applicant files Affidavit confirming service and publication | 15 | 2025-11-12 | 5 | 2025-11-05 | 7 | 2025-11-04
| 7 | Interventions Close | 40 | 2025-12-08 | 20 | 2025-11-17 | 20 | 2025-11-17
| 8 | OEB issues Procedural Order No. 1 | 60 | 2026-01-12 | 45 | 2025-12-12 | 24 | 2025-11-21
Confidentiality | 12 | OEB staff and intervenors to file submissions on confidentiality, if any |  |  | 52 | 2025-12-19 | 31 | 2025-11-28
HOLIDAY BREAK (DECEMBER 20, 2025 TO JANUARY 4, 2026 INCLUSIVE – 16 DAYS)
|  | Applicant to file reply submissions on confidentiality |  |  | 57 | 2026-01-09
|  | OEB Staff Files proposed Issues List | 70 | 2026-01-22 | 61 | 2026-01-13
Discovery | 15 | OEB staff and intervenors file the first set of interrogatories | 90 | 2026-02-11 | 70 | 2026-01-22 | 70 | 2026-01-22 | Petar on vacation Jan 15-25
|  | OEB staff and intervenor letters on intention to submit expert evidence |  |  | 78 | 2026-01-30
| 16 | Applicant files responses to the first set of interrogatories | 120 | 2026-03-13 | 99 | 2026-02-20 | 99 | 2026-02-20 | February 16 - Family
| 17 | OEB staff and intervenors to file topic areas and time estimates for Technical Conference |  |  | 109 | 2026-03-02
| 18 | Technical Conference | 130 | 2026-03-23 | 112 | 2026-03-05
| 19 | Technical Conference ends (5 days) |  |  | 118 | 2026-03-11
| 20 | Applicant files the 2025 actual information as directed in Procedural No. 1 |  |  | 118 | 2026-03-11 |  |  | ***Everything has to be finalized for Pauline to review***This is a separate process to accommodate the delay in providing the updated DVA Continuity Schedule and other items
MARCH BREAK (March 16-20, 2026 )
| 21 | OEB staff and intervenors file the second set of interrogatories |  |  | 132 | 2026-03-25
| 22 | Alectra files undertaking responses related to the Technical Conference |  |  | 134 | 2026-03-27 | #REF! | #REF!
| 23 | OEB staff and intervenors file motions letter on the first set of interrogatories and undertakings |  |  | 139 | 2026-04-01
| 24 | Motions Hearing held (Re Incomplete IRRs & Undertakings) |  |  | 140 | 2026-04-02 |  |  | April 3 is Good Friday
| 25 | Alectra files responses to the second set of interrogatories |  |  | 146 | 2026-04-08 |  |  | Alectra needs 2 weeks
| 26 | OEB staff and intervenors file expert evidence, if any | 140 | 2026-04-02 | 148 | 2026-04-10
| 27 | OEB and Intervenors file clarification questions on the second set of IRs. |  |  | 153 | 2026-04-15
| 28 | Interrogatories on OEB staff/intervenor expert evidence | 147 | 2026-04-09 | 155 | 2026-04-17 | #REF! | #REF!
| 29 | Alectra Utilities files responses to the clarification questions on the second set of interrogatory responses |  |  | 160 | 2026-04-22
| 30 | OEB staff and intervenor responses to interrogatories on expert evidence filed | 155 | 2026-04-17 | 162 | 2026-04-24 | #REF! | #REF!
Scenario 1 - Substantial Settlement (1 Week Hearing)
| 31 | Settlement Conference begins | 165 | 2026-04-27 | 167 | 2026-04-29 | 167 | 2026-04-29
| 32 | Settlement Conference ends |  |  | 173 | 2026-05-05 | 173 | 2026-05-05
| 33 | Settlement Progress Letter filed |  |  | 173 | 2026-05-05 | 173 | 2026-05-05
| 34 | Potential additional settlement days begin |  |  | 174 | 2026-05-06 | 2026-05-22 | 2026-06-07
| 35 | Potential additional settlement days end |  |  | 176 | 2026-05-08
| 36 | Settlement Proposal filed (SUBSTANTIAL Settlement) | 180 | 2026-05-12 | 194 | 2026-05-26 | 194 | 2026-05-26 | May 18 is Victoria Day
| 37 | OEB staff submission on settlement proposal filed | 187 | 2026-05-19 | 204 | 2026-06-05 | 204 | 2026-06-05
| 38 | Presentation of settlement agreement & oral hearing on unsettled issues begins (5 Days) | 200 | 2026-06-01 | 214 | 2026-06-15 | 214 | 2026-06-15
| 39 | Oral Hearing ends |  |  | 218 | 2026-06-19 | 218 | 2026-06-19
| 40 | Undertakings from Oral Hearing filed |  |  | 225 | 2026-06-26 | 225 | 2026-06-26
| 41 | Argument-in-chief filed | 230 | 2026-07-02 | 230 | 2026-07-02 | 230 | 2026-07-01 | July 1 is Canada Day
| 42 | OEB staff and intervenor submissions filed | 250 | 2026-07-21 | 250 | 2026-07-21 | 250 | 2026-07-21
| 43 | Reply argument filed | 265 | 2026-08-05 | 265 | 2026-08-05 | 265 | 2026-08-05 | Aug 3 is Civic Day
| 44 | Decision issued | 355 | 2026-11-03 | 355 | 2026-11-03 | 355 | 2026-11-03
Scenario 2 - No Settlement (3.5 Week Hearing)
| 31 | Settlement Conference begins | 165 | 2026-04-27 | 167 | 2026-04-29 | 167 | 2026-04-29
| 32 | Settlement Conference ends |  |  | 173 | 2026-05-05 | 173 | 2026-05-05
| 33 | Letter reporting no settlement filed | 180 | 2026-05-12 | 173 | 2026-05-05 | 173 | 2026-05-05
| 34 | Oral Hearing on ALL Issues begins (3.5 weeks) | 200 | 2026-06-01 | 193 | 2026-05-25 | 193 | 2026-05-25 | May 18 is Victoria Day
| 35 | Oral Hearing Ends |  |  | 217 | 2026-06-18 | 217 | 2026-06-18
| 36 | Undertakings from Oral Hearing filed |  |  | 224 | 2026-06-25 | 224 | 2026-06-25
| 37 | Argument-in-chief filed | 230 | 2026-07-02 | 230 | 2026-07-02 | 230 | 2026-07-01 | July 1 is Canada Day
| 38 | OEB staff and intervenor Submissions filed | 250 | 2026-07-21 | 250 | 2026-07-21 | 250 | 2026-07-21
| 39 | Reply Argument filed | 265 | 2026-08-05 | 265 | 2026-08-05 | 265 | 2026-08-05 | Aug 3 is Civic Day
| 40 | Decision issued | 355 | 2026-11-03 | 355 | 2026-11-03 | 355 | 2026-11-03
Scenario 3 - Partial Settlement (2 Week Hearing)
| 31 | Settlement Conference begins | 165 | 2026-04-27 | 167 | 2026-04-29 | 167 | 2026-04-29
| 32 | Settlement Conference ends |  |  | 173 | 2026-05-05 | 173 | 2026-05-05
| 33 | Settlement Progress Letter filed |  |  | 173 | 2026-05-05 | 173 | 2026-05-05
| 34 | Potential additional settlement days begin |  |  | 174 | 2026-05-06
| 35 | Potential additional settlement days end |  |  | 176 | 2026-05-08
| 36 | Settlement Proposal filed (PARTIAL Settlement) | 180 | 2026-05-12 | 189 | 2026-05-21 | 189 | 2026-05-21 | May 18 is Victoria Day
| 37 | OEB staff submission on Settlement Proposal filed | 187 | 2026-05-19 | 196 | 2026-05-28 | 196 | 2026-05-28
| 38 | Presentation of Settlement Agreement & Oral Hearing on unsettled issues begins (2 weeks) | 200 | 2026-06-01 | 207 | 2026-06-08 | 207 | 2026-06-08
| 39 | Oral Hearing Ends/Decision on Settlement Agreement |  |  | 221 | 2026-06-22 | 221 | 2026-06-22
| 40 | Undertakings from Oral Hearing filed |  |  | 228 | 2026-06-29 | 228 | 2026-06-29
| 41 | Argument-in-chief filed | 230 | 2026-07-02 | 230 | 2026-07-02 | 230 | 2026-07-01 | July 1 is Canada Day
| 42 | OEB staff and intervenor submissions filed | 250 | 2026-07-21 | 250 | 2026-07-21 | 250 | 2026-07-21
| 43 | Reply argument filed | 265 | 2026-08-05 | 265 | 2026-08-05 | 265 | 2026-08-05 | Aug 3 is Civic Day
| 44 | Decision issued | 355 | 2026-11-03 | 355 | 2026-11-03 | 355 | 2026-11-03
Scenario 4 - Full Settlement
| 31 | Settlement Conference begins | 165 | 2026-04-27 | 167 | 2026-04-29 | 158 | 2026-04-20
| 32 | Settlement Conference ends |  |  | 173 | 2026-05-05 | 162 | 2026-04-24
| 33 | Settlement Progress Letter filed |  |  | 173 | 2026-05-05 | 166 | 2026-04-28
| 34 | Settlement Conference continues (3 additional days if required) |  |  | 174 | 2026-05-06
| 35 | Potential additional settlement days end |  |  | 176 | 2026-05-08
| 36 | Settlement Proposal filed (FULL settlement) | 180 | 2026-05-12 | 194 | 2026-05-26 | 183 | 2026-05-15
| 37 | OEB staff submission on Settlement Proposal filed | 187 | 2026-05-19 | 204 | 2026-06-05 | 204 | 2026-06-05
| 38 | Decision issued | 355 | 2026-11-03 | 295 | 2026-09-04 | 295 | 2026-09-04
Notes:
* Indicative dates have not been approved by the OEB Panel. They are intended to be illustrative only, provided the individual steps take place.
Formulas:
Performance Standard Date = [Performance Standard Days Elapsed]+G7
Performance Standard Date = [Performance Standard Days Elapsed]+G7+1
Note on I11: Narisa Jotiban: PO1 can be issued on November 21, instead of 24 if there is no objection for intervenor requests from Alectra

## Test Scenario 1 (hidden)
Illustrative Schedule for Alectra Utilities - 2027-2031 Custom IR Application
OEB File Number: EB-2025-0252
Updated: November 26, 2025
Stage | Step # | Procedural Steps | Performance Standard Days Elapsed | Performance Standard Date | Case Schedule Days Elapsed | Case Schedule Indicative Date* (Scenario 1) | Planned Case Schedule Days Elapsed | Case Schedule Indicative Date* (Scenario 2)
Completeness | 1 | Applicant files Application |  |  |  | 2025-10-14
| 2 | OEB issues Acknowledgement Letter |  |  |  | 2025-10-15
| 3 | OEB issues Completeness Letter |  |  | 0 | 2025-10-28
Notice & Procedural Order No. 1 | 4 | OEB issues Notice of Hearing | 10 | 2025-11-07 | 3 | 2025-10-31 | 3 | 2025-10-31
| 6 | Applicant files Affidavit confirming service and publication | 15 | 2025-11-12 | 5 | 2025-11-05 | 7 | 2025-11-04
| 7 | Interventions Close | 40 | 2025-12-08 | 20 | 2025-11-17 | 20 | 2025-11-17
| 8 | OEB issues Procedural Order No. 1 | 60 | 2026-01-12 | 51 | 2025-12-18 | 24 | 2025-11-21
HOLIDAY BREAK (DECEMBER 20, 2025 TO JANUARY 4, 2026 INCLUSIVE – 16 DAYS)
Issues List | 9 | OEB Staff Files proposed Issues List | 70 | 2026-01-22 | 60 | 2026-01-12
Confidentiality | 12 | OEB staff and intervenors to file submissions on confidentiality, if any |  |  | 60 | 2026-01-12
| 13 | Applicant to file reply submissions on confidentiality |  |  | 67 | 2026-01-19
Intervenor/Staff Intent Letter on Expert Evidence | 14 | OEB staff and intervenor letters on intention to submit expert evidence |  |  | 78 | 2026-01-30
Discovery | 15 | OEB staff and intervenors file the first set of interrogatories | 90 | 2026-02-11 | 70 | 2026-01-22 | 70 | 2026-01-22
| 16 | Applicant files responses to the first set of interrogatories | 120 | 2026-03-13 | 99 | 2026-02-20 | 99 | 2026-02-20 | February 16 - Family
| 17 | OEB staff and intervenors to file topic areas and time estimates for Technical Conference |  |  | 109 | 2026-03-02
| 18 | Technical Conference | 130 | 2026-03-23 | 112 | 2026-03-05
| 19 | Technical Conference ends (5 days) |  |  | 118 | 2026-03-11
| 20 | Applicant files the 2025 actual information as directed in Procedural No. 1 |  |  | 118 | 2026-03-11 |  |  | ***Everything has to be finalized for Pauline to review***This is a separate process to accommodate the delay in providing the updated DVA Continuity Schedule and other items
MARCH BREAK (March 16-20, 2026 )
| 21 | OEB staff and intervenors file the second set of interrogatories |  |  | 132 | 2026-03-25
| 22 | Alectra files undertaking responses related to the Technical Conference |  |  | 134 | 2026-03-27 | #REF! | #REF!
| 23 | OEB staff and intervenors file motions letter on the first set of interrogatories and undertakings |  |  | 139 | 2026-04-01
| 24 | Motions Hearing held (Re Incomplete IRRs & Undertakings) |  |  | 140 | 2026-04-02 |  |  | April 3 is Good Friday
| 25 | Alectra files responses to the second set of interrogatories |  |  | 146 | 2026-04-08 |  |  | Alectra needs 2 weeks
| 26 | OEB staff and intervenors file expert evidence, if any | 140 | 2026-04-02 | 148 | 2026-04-10
| 27 | OEB and Intervenors file clarification questions on the second set of IRs. |  |  | 153 | 2026-04-15
| 28 | Interrogatories on OEB staff/intervenor expert evidence | 147 | 2026-04-09 | 155 | 2026-04-17 | #REF! | #REF!
| 29 | Alectra Utilities files responses to the clarification questions on the second set of interrogatory responses |  |  | 160 | 2026-04-22
| 30 | OEB staff and intervenor responses to interrogatories on expert evidence filed | 155 | 2026-04-17 | 162 | 2026-04-24 | #REF! | #REF!
Scenario 1 - Substantial Settlement (1 Week Hearing)
| 31 | Settlement Conference begins | 165 | 2026-04-27 | 167 | 2026-04-29 | 167 | 2026-04-29
| 32 | Settlement Conference ends |  |  | 173 | 2026-05-05 | 173 | 2026-05-05
| 33 | Settlement Progress Letter filed |  |  | 173 | 2026-05-05 | 173 | 2026-05-05
| 34 | Potential additional settlement days begin |  |  | 174 | 2026-05-06 | 2026-05-22 | 2026-06-07
| 35 | Potential additional settlement days end |  |  | 176 | 2026-05-08
| 36 | Settlement Proposal filed (SUBSTANTIAL Settlement) | 180 | 2026-05-12 | 194 | 2026-05-26 | 194 | 2026-05-26 | May 18 is Victoria Day
| 37 | OEB staff submission on settlement proposal filed | 187 | 2026-05-19 | 204 | 2026-06-05 | 204 | 2026-06-05
| 38 | Presentation of settlement agreement & oral hearing on unsettled issues begins (5 Days) | 200 | 2026-06-01 | 214 | 2026-06-15 | 214 | 2026-06-15
| 39 | Oral Hearing ends |  |  | 218 | 2026-06-19 | 218 | 2026-06-19
| 40 | Undertakings from Oral Hearing filed |  |  | 225 | 2026-06-26 | 225 | 2026-06-26
| 41 | Argument-in-chief filed | 230 | 2026-07-02 | 230 | 2026-07-02 | 230 | 2026-07-01 | July 1 is Canada Day
| 42 | OEB staff and intervenor submissions filed | 250 | 2026-07-21 | 250 | 2026-07-21 | 250 | 2026-07-21
| 43 | Reply argument filed | 265 | 2026-08-05 | 265 | 2026-08-05 | 265 | 2026-08-05 | Aug 3 is Civic Day
| 44 | Decision issued | 355 | 2026-11-03 | 355 | 2026-11-03 | 355 | 2026-11-03
Scenario 2 - No Settlement (3.5 Week Hearing)
| 31 | Settlement Conference begins | 165 | 2026-04-27 | 167 | 2026-04-29 | 167 | 2026-04-29
| 32 | Settlement Conference ends |  |  | 173 | 2026-05-05 | 173 | 2026-05-05
| 33 | Letter reporting no settlement filed | 180 | 2026-05-12 | 173 | 2026-05-05 | 173 | 2026-05-05
| 34 | Oral Hearing on ALL Issues begins (3.5 weeks) | 200 | 2026-06-01 | 193 | 2026-05-25 | 193 | 2026-05-25 | May 18 is Victoria Day
| 35 | Oral Hearing Ends |  |  | 217 | 2026-06-18 | 217 | 2026-06-18
| 36 | Undertakings from Oral Hearing filed |  |  | 224 | 2026-06-25 | 224 | 2026-06-25
| 37 | Argument-in-chief filed | 230 | 2026-07-02 | 230 | 2026-07-02 | 230 | 2026-07-01 | July 1 is Canada Day
| 38 | OEB staff and intervenor Submissions filed | 250 | 2026-07-21 | 250 | 2026-07-21 | 250 | 2026-07-21
| 39 | Reply Argument filed | 265 | 2026-08-05 | 265 | 2026-08-05 | 265 | 2026-08-05 | Aug 3 is Civic Day
| 40 | Decision issued | 355 | 2026-11-03 | 355 | 2026-11-03 | 355 | 2026-11-03
Scenario 3 - Partial Settlement (2 Week Hearing)
| 31 | Settlement Conference begins | 165 | 2026-04-27 | 167 | 2026-04-29 | 167 | 2026-04-29
| 32 | Settlement Conference ends |  |  | 173 | 2026-05-05 | 173 | 2026-05-05
| 33 | Settlement Progress Letter filed |  |  | 173 | 2026-05-05 | 173 | 2026-05-05
| 34 | Potential additional settlement days begin |  |  | 174 | 2026-05-06
| 35 | Potential additional settlement days end |  |  | 176 | 2026-05-08
| 36 | Settlement Proposal filed (PARTIAL Settlement) | 180 | 2026-05-12 | 189 | 2026-05-21 | 189 | 2026-05-21 | May 18 is Victoria Day
| 37 | OEB staff submission on Settlement Proposal filed | 187 | 2026-05-19 | 196 | 2026-05-28 | 196 | 2026-05-28
| 38 | Presentation of Settlement Agreement & Oral Hearing on unsettled issues begins (2 weeks) | 200 | 2026-06-01 | 207 | 2026-06-08 | 207 | 2026-06-08
| 39 | Oral Hearing Ends/Decision on Settlement Agreement |  |  | 221 | 2026-06-22 | 221 | 2026-06-22
| 40 | Undertakings from Oral Hearing filed |  |  | 228 | 2026-06-29 | 228 | 2026-06-29
| 41 | Argument-in-chief filed | 230 | 2026-07-02 | 230 | 2026-07-02 | 230 | 2026-07-01 | July 1 is Canada Day
| 42 | OEB staff and intervenor submissions filed | 250 | 2026-07-21 | 250 | 2026-07-21 | 250 | 2026-07-21
| 43 | Reply argument filed | 265 | 2026-08-05 | 265 | 2026-08-05 | 265 | 2026-08-05 | Aug 3 is Civic Day
| 44 | Decision issued | 355 | 2026-11-03 | 355 | 2026-11-03 | 355 | 2026-11-03
Scenario 4 - Full Settlement
| 31 | Settlement Conference begins | 165 | 2026-04-27 | 167 | 2026-04-29 | 158 | 2026-04-20
| 32 | Settlement Conference ends |  |  | 173 | 2026-05-05 | 162 | 2026-04-24
| 33 | Settlement Progress Letter filed |  |  | 173 | 2026-05-05 | 166 | 2026-04-28
| 34 | Settlement Conference continues (3 additional days if required) |  |  | 174 | 2026-05-06
| 35 | Potential additional settlement days end |  |  | 176 | 2026-05-08
| 36 | Settlement Proposal filed (FULL settlement) | 180 | 2026-05-12 | 194 | 2026-05-26 | 183 | 2026-05-15
| 37 | OEB staff submission on Settlement Proposal filed | 187 | 2026-05-19 | 204 | 2026-06-05 | 204 | 2026-06-05
| 38 | Decision issued | 355 | 2026-11-03 | 295 | 2026-09-04 | 295 | 2026-09-04
Notes:
* Indicative dates have not been approved by the OEB Panel. They are intended to be illustrative only, provided the individual steps take place.
Formulas:
Performance Standard Date = [Performance Standard Days Elapsed]+G7
Performance Standard Date = [Performance Standard Days Elapsed]+G7+1
Note on I11: Narisa Jotiban: PO1 can be issued on November 21, instead of 24 if there is no objection for intervenor requests from Alectra

## Test Scenario 1 (2) (hidden)
Illustrative Schedule for Alectra Utilities - 2027-2031 Custom IR Application
OEB File Number: EB-2025-0252
Updated: November 26, 2025
Stage | Step # | Procedural Steps | Performance Standard Days Elapsed | Performance Standard Date | Case Schedule Days Elapsed | Case Schedule Indicative Date* (Scenario 1) | Planned Case Schedule Days Elapsed | Case Schedule Indicative Date* (Scenario 2)
Completeness | 1 | Applicant files Application |  |  |  | 2025-10-14
| 2 | OEB issues Acknowledgement Letter |  |  |  | 2025-10-15
| 3 | OEB issues Completeness Letter |  |  | 0 | 2025-10-28
Notice & Procedural Order No. 1 | 4 | OEB issues Notice of Hearing | 10 | 2025-11-07 | 3 | 2025-10-31 | 3 | 2025-10-31
| 6 | Applicant files Affidavit confirming service and publication | 15 | 2025-11-12 | 5 | 2025-11-05 | 7 | 2025-11-04
| 7 | Interventions Close | 40 | 2025-12-08 | 20 | 2025-11-17 | 20 | 2025-11-17
| 8 | OEB issues Procedural Order No. 1 | 60 | 2026-01-12 | 51 | 2025-12-18 | 24 | 2025-11-21
HOLIDAY BREAK (DECEMBER 20, 2025 TO JANUARY 4, 2026 INCLUSIVE – 16 DAYS)
Issues List | 9 | OEB Staff Files proposed Issues List | 70 | 2026-01-22 | 60 | 2026-01-12
Confidentiality | 12 | OEB staff and intervenors to file submissions on confidentiality, if any |  |  | 60 | 2026-01-12
| 13 | Applicant to file reply submissions on confidentiality |  |  | 67 | 2026-01-19
Intervenor/Staff Intent Letter on Expert Evidence | 14 | OEB staff and intervenor letters on intention to submit expert evidence |  |  | 78 | 2026-01-30
Discovery | 15 | OEB staff and intervenors file the first set of interrogatories | 90 | 2026-02-11 | 70 | 2026-01-22 | 70 | 2026-01-22
| 16 | Applicant files responses to the first set of interrogatories | 120 | 2026-03-13 | 99 | 2026-02-20 | 99 | 2026-02-20 | February 16 - Family
| 17 | OEB staff and intervenors to file topic areas and time estimates for Technical Conference |  |  | 109 | 2026-03-02
| 18 | Technical Conference | 130 | 2026-03-23 | 112 | 2026-03-05
| 19 | Technical Conference ends (5 days) |  |  | 118 | 2026-03-11
| 20 | Applicant files the 2025 actual information as directed in Procedural No. 1 |  |  | 118 | 2026-03-11 |  |  | ***Everything has to be finalized for Pauline to review***This is a separate process to accommodate the delay in providing the updated DVA Continuity Schedule and other items
MARCH BREAK (March 16-20, 2026 )
| 21 | OEB staff and intervenors file the second set of interrogatories |  |  | 132 | 2026-03-25
| 22 | Alectra files undertaking responses related to the Technical Conference |  |  | 134 | 2026-03-27 | #REF! | #REF!
| 23 | OEB staff and intervenors file motions letter on the first set of interrogatories and undertakings |  |  | 139 | 2026-04-01
| 24 | Motions Hearing held (Re Incomplete IRRs & Undertakings) |  |  | 140 | 2026-04-02 |  |  | April 3 is Good Friday
| 25 | Alectra files responses to the second set of interrogatories |  |  | 146 | 2026-04-08 |  |  | Alectra needs 2 weeks
| 26 | OEB staff and intervenors file expert evidence, if any | 140 | 2026-04-02 | 148 | 2026-04-10
| 27 | OEB and Intervenors file clarification questions on the second set of IRs. |  |  | 153 | 2026-04-15
| 28 | Interrogatories on OEB staff/intervenor expert evidence | 147 | 2026-04-09 | 155 | 2026-04-17 | #REF! | #REF!
| 29 | Alectra Utilities files responses to the clarification questions on the second set of interrogatory responses |  |  | 160 | 2026-04-22
| 30 | OEB staff and intervenor responses to interrogatories on expert evidence filed | 155 | 2026-04-17 | 162 | 2026-04-24 | #REF! | #REF!
Scenario 1 - Substantial Settlement (1 Week Hearing)
| 31 | Settlement Conference begins | 165 | 2026-04-27 | 167 | 2026-04-29 | 167 | 2026-04-29
| 32 | Settlement Conference ends |  |  | 173 | 2026-05-05 | 173 | 2026-05-05
| 33 | Settlement Progress Letter filed |  |  | 173 | 2026-05-05 | 173 | 2026-05-05
| 34 | Potential additional settlement days begin |  |  | 174 | 2026-05-06 | 2026-05-22 | 2026-06-07
| 35 | Potential additional settlement days end |  |  | 176 | 2026-05-08
| 36 | Settlement Proposal filed (SUBSTANTIAL Settlement) | 180 | 2026-05-12 | 194 | 2026-05-26 | 194 | 2026-05-26 | May 18 is Victoria Day
| 37 | OEB staff submission on settlement proposal filed | 187 | 2026-05-19 | 204 | 2026-06-05 | 204 | 2026-06-05
| 38 | Presentation of settlement agreement & oral hearing on unsettled issues begins (5 Days) | 200 | 2026-06-01 | 214 | 2026-06-15 | 214 | 2026-06-15
| 39 | Oral Hearing ends |  |  | 218 | 2026-06-19 | 218 | 2026-06-19
| 40 | Undertakings from Oral Hearing filed |  |  | 225 | 2026-06-26 | 225 | 2026-06-26
| 41 | Argument-in-chief filed | 230 | 2026-07-02 | 230 | 2026-07-02 | 230 | 2026-07-01 | July 1 is Canada Day
| 42 | OEB staff and intervenor submissions filed | 250 | 2026-07-21 | 250 | 2026-07-21 | 250 | 2026-07-21
| 43 | Reply argument filed | 265 | 2026-08-05 | 265 | 2026-08-05 | 265 | 2026-08-05 | Aug 3 is Civic Day
| 44 | Decision issued | 355 | 2026-11-03 | 355 | 2026-11-03 | 355 | 2026-11-03
Scenario 2 - No Settlement (3.5 Week Hearing)
| 31 | Settlement Conference begins | 165 | 2026-04-27 | 167 | 2026-04-29 | 167 | 2026-04-29
| 32 | Settlement Conference ends |  |  | 173 | 2026-05-05 | 173 | 2026-05-05
| 33 | Letter reporting no settlement filed | 180 | 2026-05-12 | 173 | 2026-05-05 | 173 | 2026-05-05
| 34 | Oral Hearing on ALL Issues begins (3.5 weeks) | 200 | 2026-06-01 | 193 | 2026-05-25 | 193 | 2026-05-25 | May 18 is Victoria Day
| 35 | Oral Hearing Ends |  |  | 217 | 2026-06-18 | 217 | 2026-06-18
| 36 | Undertakings from Oral Hearing filed |  |  | 224 | 2026-06-25 | 224 | 2026-06-25
| 37 | Argument-in-chief filed | 230 | 2026-07-02 | 230 | 2026-07-02 | 230 | 2026-07-01 | July 1 is Canada Day
| 38 | OEB staff and intervenor Submissions filed | 250 | 2026-07-21 | 250 | 2026-07-21 | 250 | 2026-07-21
| 39 | Reply Argument filed | 265 | 2026-08-05 | 265 | 2026-08-05 | 265 | 2026-08-05 | Aug 3 is Civic Day
| 40 | Decision issued | 355 | 2026-11-03 | 355 | 2026-11-03 | 355 | 2026-11-03
Scenario 3 - Partial Settlement (2 Week Hearing)
| 31 | Settlement Conference begins | 165 | 2026-04-27 | 167 | 2026-04-29 | 167 | 2026-04-29
| 32 | Settlement Conference ends |  |  | 173 | 2026-05-05 | 173 | 2026-05-05
| 33 | Settlement Progress Letter filed |  |  | 173 | 2026-05-05 | 173 | 2026-05-05
| 34 | Potential additional settlement days begin |  |  | 174 | 2026-05-06
| 35 | Potential additional settlement days end |  |  | 176 | 2026-05-08
| 36 | Settlement Proposal filed (PARTIAL Settlement) | 180 | 2026-05-12 | 189 | 2026-05-21 | 189 | 2026-05-21 | May 18 is Victoria Day
| 37 | OEB staff submission on Settlement Proposal filed | 187 | 2026-05-19 | 196 | 2026-05-28 | 196 | 2026-05-28
| 38 | Presentation of Settlement Agreement & Oral Hearing on unsettled issues begins (2 weeks) | 200 | 2026-06-01 | 207 | 2026-06-08 | 207 | 2026-06-08
| 39 | Oral Hearing Ends/Decision on Settlement Agreement |  |  | 221 | 2026-06-22 | 221 | 2026-06-22
| 40 | Undertakings from Oral Hearing filed |  |  | 228 | 2026-06-29 | 228 | 2026-06-29
| 41 | Argument-in-chief filed | 230 | 2026-07-02 | 230 | 2026-07-02 | 230 | 2026-07-01 | July 1 is Canada Day
| 42 | OEB staff and intervenor submissions filed | 250 | 2026-07-21 | 250 | 2026-07-21 | 250 | 2026-07-21
| 43 | Reply argument filed | 265 | 2026-08-05 | 265 | 2026-08-05 | 265 | 2026-08-05 | Aug 3 is Civic Day
| 44 | Decision issued | 355 | 2026-11-03 | 355 | 2026-11-03 | 355 | 2026-11-03
Scenario 4 - Full Settlement
| 31 | Settlement Conference begins | 165 | 2026-04-27 | 167 | 2026-04-29 | 158 | 2026-04-20
| 32 | Settlement Conference ends |  |  | 173 | 2026-05-05 | 162 | 2026-04-24
| 33 | Settlement Progress Letter filed |  |  | 173 | 2026-05-05 | 166 | 2026-04-28
| 34 | Settlement Conference continues (3 additional days if required) |  |  | 174 | 2026-05-06
| 35 | Potential additional settlement days end |  |  | 176 | 2026-05-08
| 36 | Settlement Proposal filed (FULL settlement) | 180 | 2026-05-12 | 194 | 2026-05-26 | 183 | 2026-05-15
| 37 | OEB staff submission on Settlement Proposal filed | 187 | 2026-05-19 | 204 | 2026-06-05 | 204 | 2026-06-05
| 38 | Decision issued | 355 | 2026-11-03 | 295 | 2026-09-04 | 295 | 2026-09-04
Notes:
* Indicative dates have not been approved by the OEB Panel. They are intended to be illustrative only, provided the individual steps take place.
Formulas:
Performance Standard Date = [Performance Standard Days Elapsed]+G7
Performance Standard Date = [Performance Standard Days Elapsed]+G7+1
Note on I11: Narisa Jotiban: PO1 can be issued on November 21, instead of 24 if there is no objection for intervenor requests from Alectra

## Toronto Hydro Hearing Schedule (hidden)
Toronto Hydro (EB-2018-0165) - PO4 - February 27, 2019
Toronto hydro files resposes to Interrogatories on Application Update | 2019-06-11
Oral hearing starts | 2019-06-27 | 16
Oral hearing ends | 2019-07-19 | 22
Toronto Hydro files argument in chief | 2019-08-02 | 14
OEB staff files submission | 2019-08-21 | 19
Intervenors file submissions | 2019-08-26 | 5
Toronto Hydro files reply submission | 2019-09-13 | 18