## Centre Wellington
Schedule for Cost of Service - Centre Wellington Hydro Limited
OEB File Number: EB-2024-0012
Updated: June 25, 2024
Stage | Step # | Procedural Steps | Performance Standard Days Elapsed | Performance Standard Date | Case Schedule Days Elapsed | Case Schedule Date Planned* | Case Schedule Date Approved | Actual Date | Status | Comments
Completeness | 1 | Applicant Files Application |  | 2024-05-02 |  |  |  | 2024-05-02 | 100%
| 2 | OEB Issues Acknowledgement Letter |  | 2024-05-03 |  |  |  | 2024-05-03 | 100%
| 3 | OEB Issues Completeness Letter |  | 2024-05-16 | 0 |  | 2024-05-16 | 2024-05-16 | 100%
Notice & Procedural Order No. 1 | 4 | OEB Issues Notice of Application | 10 | 2024-05-27 | 1 |  | 2024-05-22 | 2024-05-22 | 100%
| 5 | Applicant Files Affidavit Confirming Service and Publication | 15 | 2024-05-31 | 7 |  | 2024-05-31 | 2024-05-28 | 100%
| 6 | Notice of Hearing Publication Date |  |  |  |  | 2024-05-30 | 2024-05-30 | 100%
| 7 | Intervention Request Close | 25 | 2024-06-10 | 25 |  | 2024-06-10 | 2024-06-10 | 100%
| 8 | OEB Issues Procedural Order No. 1 | 35 | 2024-06-20 | 28 |  | 2024-06-13 | 2024-06-13 | 100%
Discovery Process | 9 | Issues List Filed | 45 | 2024-07-02 | 39 |  | 2024-06-24 | 2024-06-24 | 100%
| 10 | Interrogatories Issued | 60 | 2024-07-15 | 57 |  | 2024-07-12
| 11 | Applicant Files Responses to Interrogatories | 80 | 2024-08-05 | 77 |  | 2024-08-01
Settlement Process | 12 | Settlement Conference (August 19-21) | 90 | 2024-08-14 | 95 |  | 2024-08-19
| 13 | Settlement Progress Letter Filed |  |  | 98 |  | 2024-08-23
| 14 | Settlement Proposal Filed | 115 | 2024-09-09 | 118 |  | 2024-09-11
| 15 | OEB Staff Submission on Settlement Proposal, if any | 122 | 2024-09-16 | 125 |  | 2024-09-18
Hearing | 16 | Oral Hearing (Including presentation of Settlement) | 130 | 2024-09-23 | 135 |  | 2024-09-30
Argument Process | 17 | Applicant Files Written Argument in Chief | 140 | 2024-10-03 | 140 | 2024-10-03
| 18 | OEB Staff and Intervenors File Submissions | 150 | 2024-10-14 | 150 | 2024-10-14
| 19 | Applicant Files Written Reply Argument | 170 | 2024-11-04 | 170 | 2024-11-04
HOLIDAY BREAK (December 21, 2024, TO January 5, 2025, INCLUSIVE – 16 DAYS)
Decision | 20 | Decision Issued | 230 | 2025-01-23 | 230 | 2025-01-21
| 21 | OEB Receives Draft Order and Tariff Sheets | 250 | 2025-01-21
| 22 | OEBstaff and Intervenors Files Comments on Draft Rate order and Tarif Sheets | 257 | 2025-01-28
| 23 | Applicant Files Reply Comments on Draft Rate order and Tarif Sheets | 264 | 2025-02-04
Rate Order | 24 | OEB Issues Rate Order and Tariff Sheets | 275 | 2025-02-15
* Planned dates have not been approved by the OEB Panel. They are intended to be illustrative only, provided the individual steps take place.
Formulas:
Performance Standard Date = [Performance Standard Days Elapsed]+I7+1
Performance Standard Date = [Performance Standard Days Elapsed]+I7
Case Schedule Date Approved = [Case Schedule Days Elapsed]+I7
Case Schedule Date Approved = [Case Schedule Days Elapsed]+I7+1
Actual Date = Table14[[#This Row],[Case Schedule Date Approved]]
Case Schedule Date Planned* = [Case Schedule Days Elapsed]+I7
Case Schedule Date Planned* = [Case Schedule Days Elapsed]+I7+1