## InnPower Corporation
Schedule for InnPower Corporation's 2024 Cost of Service Application
OEB File Number: EB-2023-0033
Updated: October 27, 2023
Stage | Step # | Procedural Steps | Performance Standard Days Elapsed | Performance Standard Date | Case Schedule Days Elapsed | Case Schedule Date Planned* | Case Schedule Date Approved | Actual Date | Status | Comments
Completeness | 1 | Applicant Files Application | [5 empty] | 2023-05-12 | 100%
| 2 | OEB Issues Acknowledgement Letter | [5 empty] | 2023-05-16 | 100%
| 3 | OEB Issues Completeness Letter |  |  | 0 |  |  | 2023-05-26 | 100%
Notice & Procedural Order No. 1 | 4 | OEB Issues Notice of Hearing | 10 | 2023-06-05 | 6 |  | 2023-06-01 | 2023-06-01 | 100%
| 5 | Notice of Hearing Publication Date |  |  |  |  | 2023-06-08 | 2023-06-08 | 100%
| 6 | Applicant Files Affidavit Confirming Service and Publication | 15 |  |  |  |  | 2023-06-08 | 100%
| 7 | Intervention Requests Close | 25 |  |  |  | 2023-06-19 | 2023-06-19 | 100%
| 8 | OEB Issues Procedural Order No. 1 | 35 | 2023-06-30 | 28 |  | 2023-06-23 | 2023-06-23 | 100%
Issues List | 9 | OEB Staff files proposed issues list | 40 | 2023-07-05 | 33 |  | 2023-06-28 | 2023-06-28 | 100%
Discovery Process | 10 | OEB Staff and Intervenors File Interrogatories | 60 | 2023-07-25 | 53 |  | 2023-07-18 | 2023-07-18 | 100%
| 11 | Applicant Files Responses to Interrogatories | 80 | 2023-08-14 | 74 |  | 2023-08-08 | 2023-08-08 | 100%
Settlement Process | 12 | Settlement Conference Held (Aug 21-23) | 90 | 2023-08-24 | 87 |  | 2023-08-21 | 2023-08-21 | 100%
| 13 | Applicant files settlement progress letter | [5 empty] | 2023-08-24 | 100%
| 14 | DEFINED EXTENSION REQUEST (SEPTEMBER 15, 2023 TO OCTOBER 13, 2023 - 29 DAYS)
| 15 | Settlement Proposal Filed | 115 | 2023-10-17 | 111 |  | 2023-10-13 | 2023-10-13 | 100% | OEB granted applicant's extension request to file settlement proposal from September 15, 2023 to October 13, 2023.
| 16 | OEB staff Submission on Settlement Proposal Filed | 122 | 2023-10-24 | 122 |  | 2023-10-24 | 2023-10-24 | 100%
Argument Process | 17 | Applicant's Argument-in-Chief Filed | 140 | 2023-11-11 | 139 | 2023-11-10
| 18 | OEB Staff and Intervenors Argument Filed | 150 | 2023-11-21 | 150 | 2023-11-21
| 19 | Applicant's Reply Argument Filed | 170 | 2023-12-11 | 170 | 2023-12-11
HOLIDAY BREAK (DECEMBER 17, 2023 TO JANUARY 6, 2024 INCLUSIVE – 23 DAYS)
Decision | 20 | Decision Issued | 230 | 2024-03-03 | 234 | 2024-03-07
* Planned dates have not been approved by the OEB Panel. They are intended to be illustrative only, provided the individual steps take place.
Formulas:
Performance Standard Date = [Performance Standard Days Elapsed]+I7
Performance Standard Date = [Performance Standard Days Elapsed]+I7+29
Case Schedule Date Approved = [Case Schedule Days Elapsed]+I7
Case Schedule Date Approved = [Case Schedule Days Elapsed]+I7+29
Case Schedule Date Planned* = [Case Schedule Days Elapsed]+I7+29
Case Schedule Date Planned* = [Case Schedule Days Elapsed]+I7+23+29