## Orangeville Hydro
Schedule for Orangeville Hydro Limited - 2024 Cost of Service
OEB File Number: EB-2023-0045
Updated: December 15, 2023
Stage | Step # | Procedural Steps | Performance Standard Days Elapsed | Performance Standard Date | Case Schedule Days Elapsed | Case Schedule Date Planned* | Case Schedule Date Approved | Actual Date | Status | Comments
Completeness | 1 | Applicant Files Application | [5 empty] | 2023-10-02 | 100%
| 2 | OEB Issues Acknowledgement Letter | [5 empty] | 2023-10-02 | 100%
| 3 | OEB Issues Completeness Letter |  | 2023-10-16 | 0 |  | 2023-10-16 | 2023-10-16 | 100%
Notice & Procedural Order No. 1 | 4 | OEB Issues Notice of Hearing | 10 | 2023-10-26 | 1 |  | 2023-10-26 | 2023-10-23 | 100%
| 5 | Applicant Files Affidavit Confirming Service and Publication | 15 | 2023-10-31 | 7 |  | 2023-10-23 | 2023-10-27 | 100%
| 6 | Notice of Hearing Publication Date |  |  | 10 |  | 2023-10-26 | 2023-10-26 | 100%
| 7 | Intervention Request Close | 25 | 2023-11-10 | 18 |  | 2023-11-03 | 2023-11-03 | 100%
| 8 | OEB Issues Procedural Order No. 1 | 35 | 2023-11-20 | 28 |  | 2023-11-13 | 2023-11-13 | 100%
Discovery Process | 9 | OEB staff Files Draft Issues List | 45 | 2023-11-30 | 38 |  | 2023-11-23 | 2023-11-17 | 100%
| 10 | OEB staff and Intervenors File Interrogatories | 60 | 2023-12-15 | 52 |  | 2023-12-07 | 2023-12-07 | 100%
HOLIDAY BREAK December 16, 2023, TO January 7, 2024, INCLUSIVE – 23 DAYS)
| 11 | Applicant Files Responses to Interrogatories | 80 | 2024-01-29 | 95 |  | 2024-01-19
Settlement Process | 12 | Settlement Conference Held (Feb 5-7) | 90 | 2024-02-06 | 112 |  | 2024-02-05
| 13 | Settlement Progress Letter Filed |  |  | 116 |  | 2024-02-09
| 14 | Settlement Proposal Filed | 115 | 2024-03-04 | 135 |  | 2024-02-28
| 15 | OEB staff Submission on Settlement Proposal Filed | 122 | 2024-03-11 | 142 |  | 2024-03-06
Hearing | 16 | Presentation of Settlement/Oral Hearing | 130 | 2024-03-18 | 149 | 2024-03-18 |  |  |  | March break: Mar 11-15
Argument Process | 17 | Applicant's Argument-in-chief Filed | 140 | 2024-03-27 | 161 | 2024-03-25
| 18 | OEB staff and Intervenor Argument Filed | 150 | 2024-04-08 | 171 | 2024-04-04
| 19 | Applicant's Reply Argument Filed | 170 | 2024-04-26 | 191 | 2024-04-24
Decision | 20 | Decision Issued | 230 | 2024-06-27 | 255 | 2024-06-27
* Planned dates have not been approved by the OEB Panel. They are intended to be illustrative only, provided the individual steps take place.
Formulas:
Performance Standard Date = [Performance Standard Days Elapsed]+I7
Performance Standard Date = [Performance Standard Days Elapsed]+I7+23+2
Case Schedule Date Approved = Table1[[#This Row],[Performance Standard Date]]
Case Schedule Date Approved = [Case Schedule Days Elapsed]+I7
Actual Date = Table1[[#This Row],[Case Schedule Date Approved]]
Case Schedule Date Planned* = I7+Table1[[#This Row],[Case Schedule Days Elapsed]]