## Watay Power
Schedule for Wataynikaneyap Power - 2025 Transmission Rates
OEB File Number: EB-2024-0176
Updated: October 29, 2024
Stage | Step # | Procedural Steps | Performance Standard Days Elapsed | Performance Standard Date | Case Schedule Days Elapsed | Case Schedule Date Planned* | Case Schedule Date Approved | Actual Date | Status | Comments
Completeness | 1 | Applicant Files Application | [5 empty] | 2024-06-28 | 100%
| 2 | OEB Issues Acknowledgement Letter | [5 empty] | 2024-07-02 | 100%
| 3 | OEB Issues Completeness Letter |  | 2024-07-12 | 0 |  | 2024-07-12 | 2024-07-12 | 100%
Notice & Procedural Order No. 1 | 4 | OEB Issues Notices | 10 | 2024-07-22 | 10 |  | 2024-07-22 | 2024-07-22 | 100%
| 5 | Applicant Files Affidavit Confirming Service and Publication | 15 | 2024-07-27 | 15 |  | 2024-07-27 | 2024-07-25 | 100%
| 6 | Notice of Hearing Publication Date |  |  | 8 |  | 2024-07-20 | 2024-07-20 | 100%
| 7 | Intervention Request Close | 25 | 2024-08-06 | 25 |  | 2024-08-06 | 2024-08-06 | 100%
| 8 | OEB Issues Procedural Order No. 1 | 35 | 2024-08-16 | 35 |  | 2024-08-16 | 2024-08-16 | 100%
Discovery | 9 | OEB staff Files Draft Issues List | 45 | 2024-08-26 | 42 |  | 2024-08-23 | 2024-08-23 | 100%
| 10 | OEB staff File Interrogatories | 60 | 2024-09-10 | 59 |  | 2024-09-09 | 2024-09-09 | 100%
| 11 | Applicant Files Responses to Interrogatories | 80 | 2024-09-30 | 77 |  | 2024-09-27 | 2024-09-27 | 100%
Settlement Process | 12 | Settlement Conference Held | 90 | 2024-10-10 | 97 |  | 2024-10-17 | 2024-10-17 | 100%
| 13 | Settlement Progress Letter Filed |  |  | 101 |  | 2024-10-21 | 2024-10-18 | 100%
| 14 | Settlement Proposal Filed | 115 | 2024-11-04 | 118 |  | 2024-11-07
| 15 | OEB staff Submission on Settlement Proposal Filed | 122 | 2024-11-11 | 122 |  | 2024-11-11
Hearing | 16 | Presentation of Settlement/Oral Hearing | 130 | 2024-11-19 | 126 | 2024-11-15
Argument Process | 17 | Applicant's Argument-in-chief Filed | 140 | 2024-11-29 | 133 | 2024-11-22
| 18 | OEB staff Argument Filed | 150 | 2024-12-09 | 140 | 2024-11-29
| 19 | Applicant's Reply Argument Filed | 170 | 2024-12-29 | 147 | 2024-12-06
Decision | 20 | Decision Issued | 230 | 2025-03-14 | 207 | 2025-02-19
* Planned dates have not been approved by the OEB Panel. They are intended to be illustrative only, provided the individual steps take place.
Formulas:
Performance Standard Date = [Performance Standard Days Elapsed]+I7
Performance Standard Date = [Performance Standard Days Elapsed]+I7+15
Case Schedule Date Approved = [Case Schedule Days Elapsed]+I7
Case Schedule Date Planned* = [Case Schedule Days Elapsed]+I7
Case Schedule Date Planned* = [Case Schedule Days Elapsed]+I7+15