## Welland Hydro
Schedule for Welland Hydro-Electric System Corp. - 2025 Cost of Service
OEB File Number: EB-2024-0058
Updated: October 29, 2024
Stage | Step # | Procedural Steps | Performance Standard Days Elapsed | Performance Standard Date | Case Schedule Days Elapsed | Case Schedule Date Planned* | Case Schedule Date Planned | Case Schedule Date Approved | Actual Date | Status | Comments
Completeness | 1 | Applicant Files Application | [6 empty] | 2024-08-26 | 100%
| 2 | OEB Issues Acknowledgement Letter | [6 empty] | 2024-08-27 | 100%
| 4 | OEB Issues Completeness Letter |  | 2024-09-09 | 0 |  |  | 2024-09-09 | 2024-09-09 | 100%
Notice & Procedural Order No. 1 | 5 | OEB Issues Notice of Hearing | 10 | 2024-09-19 | 10 |  |  | 2024-09-19 | 2024-09-19 | 100%
| 6 | Applicant Files Affidavit Confirming Service and Publication | 15 | 2024-09-24 | 17 |  |  | 2024-09-26 | 2024-09-26 | 100%
| 7 | Notice of Hearing Publication Date |  |  | 16 |  |  | 2024-09-25 | 2024-09-25 | 100%
| 8 | Intervention Requests Close | 25 | 2024-10-04 | 28 |  |  | 2024-10-07 | 2024-10-07 | 100%
| 9 | OEB Issues Procedural Order No. 1 | 35 | 2024-10-14 | 30 |  |  | 2024-10-09 | 2024-10-09 | 100%
Discovery Process | 10 | OEB Staff Files proposed Issues List | 45 | 2024-10-25 | 39 |  |  | 2024-10-18 | 2024-10-18 | 100%
| 11 | OEB Staff and Intervenors Files Interrogatories | 60 | 2024-11-08 | 53 |  |  | 2024-11-01
| 12 | Applicant Files Responses to Interrogatories | 80 | 2024-11-29 | 73 |  |  | 2024-11-21
Settlement Process | 13 | Settlement Conference Held (Dec 4-6 ) | 90 | 2024-12-09 | 86 |  |  | 2024-12-04
| 14 | Applicant files Settlement Progress Letter |  |  | 92 |  |  | 2024-12-10
| 15 | Settlement Proposal Filed | 115 | 2025-01-17 | 126 |  |  | 2025-01-13
| 16 | OEB Staff Submission on Settlement Proposal Filed | 122 | 2025-01-24 | 133 |  |  | 2025-01-20
Hearing | 17 | Presentation of Settlement/Oral Hearing | 130 | 2025-02-01 | 140 |  |  | 2025-01-27
Argument Process | 18 | Applicant's Argument-in-chief Filed | 140 | 2025-02-11 | 150 |  | 2025-02-06
| 19 | OEB Staff and Intervenor Argument Filed | 150 | 2025-02-21 | 160 |  | 2025-02-16
| 20 | Applicant's Reply Argument Filed | 170 | 2025-03-13 | 180 |  | 2025-05-08
Decision | 21 | Decision Issued | 230 | 2025-05-15 | 245 |  | 2024-05-13
* Planned dates have not been approved by the OEB Panel. They are intended to be illustrative only, provided the individual steps take place.
Formulas:
Performance Standard Date = [Performance Standard Days Elapsed]+J7
Performance Standard Date = [Performance Standard Days Elapsed]+J7+1
Case Schedule Date Approved = [Actual Date, row above]+Table1[[#This Row],[Case Schedule Days Elapsed]]
Case Schedule Date Approved = J7+Table1[[#This Row],[Case Schedule Days Elapsed]]