## Lakefront Utilities
Lakefront Utilities Inc. - 2027 Cost of Service
OEB File Number: EB-2026-0054
Updated: September 10, 2026
Stage | Step # | Procedural Steps | Performance Standard Days Elapsed | Performance Standard Date | Case Schedule Days Elapsed | Case Schedule Date Planned | Proposed Case Schedule Dates | Actual Date | Status | Comments
Completeness | 1 | Applicant Files Application | [5 empty] | 2026-06-26 | 100%
| 2 | OEB Issues Acknowledgement Letter | [5 empty] | 2026-06-26 | 100%
| 4 | OEB Issues Completeness Letter | 0 | 2026-07-10 | 0 |  | 2026-07-10 | 2026-07-10 | 100%
Notice & Procedural Order No. 1 | 5 | OEB Issues Notice of Hearing | 10 | 2026-07-20 | 10 |  | 2026-07-20 | 2026-07-20 | 100%
| 6 | Applicant Files Affidavit Confirming Service and Publication | 15 | 2026-07-27 | 15 |  | 2026-07-27 | 2026-07-27 | 100%
| 7 | Notice of Hearing Publication Date |  |  | 14 |  | 2026-07-24 | 2026-07-24 | 100%
| 8 | Intervention Requests Close | 25 | 2026-08-04 | 31 |  | 2026-08-10 | 2026-08-10 | 100%
| 9 | OEB Issues Procedural Order No. 1 | 35 | 2026-08-14 | 35 |  | 2026-08-14 | 2026-08-14 | 100%
Discovery Process | 10 | OEB Staff Files proposed Issues List | 45 | 2026-08-24 | 42 |  | 2026-08-21 | 2026-08-21 | 100%
| 11 | OEB Staff and Intervenors Files Interrogatories | 60 | 2026-09-08 | 55 |  | 2026-09-03 | 2026-09-03 | 100%
| 12 | Applicant Files Responses to Interrogatories | 80 | 2026-09-28 | 69 |  | 2026-09-17
Settlement Process | 13 | Settlement Conference Held (Sept. 23-25) | 90 | 2026-10-08 | 75 |  | 2026-09-23
| 14 | Applicant files Settlement Progress Letter |  |  | 80 |  | 2026-09-28
| 15 | Settlement Proposal Filed | 115 | 2026-11-02 | 101 |  | 2026-10-19
| 16 | OEB Staff Submission on Settlement Proposal Filed | 122 | 2026-11-09 | 108 |  | 2026-10-26
Hearing | 17 | Presentation of Settlement/Oral Hearing | 130 | 2026-11-17 | 116 |  | 2026-11-03
Argument Process | 18 | Applicant's Argument-in-chief Filed | 140 | 2026-11-27 | 123 |  | 2026-11-10
| 19 | OEB Staff and Intervenor Argument Filed | 150 | 2026-12-07 | 130 |  | 2026-11-17
| 20 | Applicant's Reply Argument Filed | 170 | 2027-01-12 | 137 |  | 2026-11-24
Decision | 21 | Decision Issued | 230 | 2027-03-15 | 197 |  | 2027-02-08
Formulas:
Performance Standard Date = [Performance Standard Days Elapsed]+I7
Performance Standard Date = [Performance Standard Days Elapsed]+I7+2
Proposed Case Schedule Dates = [Case Schedule Days Elapsed]+I7
Proposed Case Schedule Dates = [Case Schedule Days Elapsed]+I7+2
Actual Date = [Performance Standard Date]
Actual Date = [Proposed Case Schedule Dates]